AIKARTHYA FOUNDATION

SkillUp Programme  •  Monitoring & Evaluation

Program Facilitator Performance Analysis

Janhvi Mishra  —  Field Activity Review

| PF | Janhvi Mishra (Active) | Window | 15-Jun to 25-Jun-2026 |
| --- | --- | --- | --- |
| Schools | 4 (assigned 16-Jun-2026) | Source | Production database (live) |
| UUID | 3f05cb21-…-0927f0dcd6b1 | By | Akash Das |

# 1. Attendance Analysis

Attendance is counted from the first check-in: 15-Jun-2026, 12:27 IST. Each school has one registered geofence point (300 m); there is one office point (Aikarthya Head Office). A check-in is an office visit or school visit by the point it matched. Where a check-out is away from a point, the day is validated by whether an observation was recorded that day.

| Date | Check-in point | Check-out |  | Field validation |
| --- | --- | --- | --- | --- |
| 15-Jun | No registered point | 16-Jun 10:18 |  | No observation — UNVERIFIED |
| 17-Jun | Adarsh (school) | 17-Jun 17:26 |  | Observations + session at Adarsh — verified |
| 18-Jun | Gyanam (school) | 19-Jun 10:22 (next day) |  | 5 observations at Gyanam — verified |
| 20-Jun | Grace (school) | 20-Jun 17:28 |  | 6 observations at Grace — verified |
| 22-Jun | Safdariya (school) | 22-Jun 16:03 (Safdariya) |  | Fully geofence-valid; observations at Safdariya |
| 24-Jun | Head Office (office) | 25-Jun 10:17 (next day) |  | Office, then observation at Safdariya — office-then-school |
| 25-Jun | Head Office (office) | 25-Jun 16:55 |  | Office, then observation at Adarsh — office-then-school |
| Metric |  |  | Value |  |
| Total attendance days (distinct check-ins) |  |  | 7 |  |
| School-visit days |  |  | 4 — 17, 18, 20, 22 Jun |  |
| Office-visit days |  |  | 2 — 24, 25 Jun |  |
| Office-then-school days |  |  | 2 — 24, 25 Jun |  |
| Unverified day (no point, no observation) |  |  | 1 — 15 Jun |  |
| Missed same-day check-outs |  |  | 2 — 18→19, 24→25 Jun |  |
| Working days with no check-in (excl. Sun 21-Jun) |  |  | 16-Jun, 23-Jun |  |
| Leaves filed / holidays in window |  |  | 0 / 0 |  |

# 2. Observation Analysis  (submitted observations only)

Counts below use the 21 submitted observations only — unsubmitted drafts are excluded as they may be abandoned. All are Cycle 1 (baseline). Observation visits are counted by observation date.

| Metric | Value |
| --- | --- |
| Submitted observations | 21 |
| Observation-visit days | 7 |
| Average observations per visit day | 3.0 |
| Distinct teachers observed | 21 |
| Average total score | 61.5 / 100 (range 43–81) |

### Submitted observations by date

| Obs date | Submitted | Avg score | School |
| --- | --- | --- | --- |
| 17-Jun | 2 | 61.0 | Adarsh Vidyalaya |
| 18-Jun | 5 | 60.4 | Gyanam |
| 19-Jun | 1 | 67.0 | Gyanam |
| 20-Jun | 6 | 66.2 | Grace Model |
| 22-Jun | 5 | 56.8 | Safdariya |
| 24-Jun | 1 | 64.0 | Safdariya |
| 25-Jun | 1 | 56.0 | Adarsh Vidyalaya |

Note: most observations were entered in the evenings — and the 17-Jun observations were recorded on 24–25 Jun, a week later. Retrospective, backdated entry increases recall error and weakens the fidelity of the baseline.

# 3. Reporting Pipeline Analysis

Every submitted observation creates a report job: queued → generating → M&E review → PF review → released (shared). The target is governed by an SLA (Service-Level Agreement) of 72 hours — the window from observation submission within which the report should be reviewed and shared with the school. The generation engine is working; delivery is not.

| Stage | Result |
| --- | --- |
| Reports generated (AI draft) | 21 of 21 submitted (100%) |
| Reports finalised (PDF) | 21 |
| Reports shared with school | 1 (4.8%) |
| Awaiting PF review / share | 20 |
| Open reports past the 72-hour SLA | 16 |

### By real date — observations vs. generation vs. sharing

Report-generation and share dates differ from observation dates, so each column below is keyed to the date that event actually occurred.

| Date | Obs submitted | Reports generated | Reports shared |
| --- | --- | --- | --- |
| 17-Jun | 2 | — | — |
| 18-Jun | 5 | — | — |
| 19-Jun | 1 | — | — |
| 20-Jun | 6 | — | — |
| 22-Jun | 5 | 3 | — |
| 23-Jun | — | 6 | — |
| 24-Jun | 1 | — | — |
| 25-Jun | 1 | 12 | 1 |
| Total | 21 | 21 | 1 |

# 4. Session-Conducted Analysis

SkillUp runs ~15–16 offline workshops and ~20–25 online sessions per year. In this window Janhvi has exactly one session recorded:

| Date | 17-Jun-2026 • Adarsh Vidyalaya (secondary) |
| --- | --- |
| Topic / Mode | “Culture — from rules to habits” • Offline workshop • Completed & submitted |
| Attendance | 11 teachers (all present) • Teacher-leader present • Engagement 3 / 5 • 75 min |

Gaps: only 1 of 4 schools has a session record. Gyanam, Grace Model and Safdariya each received multiple observations but have no session logged — either sessions were conducted but not recorded, or not conducted at all. The one logged session is fully detailed, so the absence elsewhere is a coverage/logging gap, not a tooling problem.

# 5. Data Quality & Validity  (submitted observations only)

Completeness across the 21 submitted observations. The graded core — the full 34-indicator rubric and the glow/grow narrative — is complete on every submitted observation. The gaps are in follow-up and evidence fields.

| Field | Filled | Assessment |
| --- | --- | --- |
| Next observation date | 0 / 21 | Breaks the monthly observation schedule |
| Classroom photo | 2 / 21 | Evidence trail largely absent |
| Student count | 15 / 21 | Engagement context missing on a third |
| Valid duration | 20 / 21 | One reversed start/end (negative duration) |
| Subject / Grade | 19 / 21 | 2 forms were incomplete previously and completed at 25-06-2026 |
| Glow / Grow narrative + 34-indicator scores | 21 / 21 | Complete |

# 6. Overall Performance Assessment  (critical)

High activity, low delivery — and the activity is worth less than it looks. Janhvi reached all four schools and produced 21 submitted observations in roughly eight working days, which is strong raw output for a PF in her first fortnight. But output is not the goal; delivered feedback is. On that measure she is failing: 20 of 21 reports never reached a school, 16 are past SLA, and only 1 teacher has actually received feedback. An observation that is scored but never shared has consumed a classroom visit and produced nothing the teacher can act on — so the real completion rate of her core job this cycle is closer to 5%, not 100%.

Three deeper concerns temper the volume. (1) The baseline is fragile: no next-observation dates, near-total absence of photo evidence, and retrospective backdated entry undermine the integrity of the Cycle-1 baseline that all later growth will be measured against. (2) Attendance is unreliable: only 1 of 7 days is fully geofence-valid and one day cannot be verified as field work at all. (3) Sessions are largely invisible: three of four schools show no session. The picture is a facilitator who is good at the in-class observation task itself but is not closing any of the loops that turn that task into programme value.

| Dimension | Rating | Basis |
| --- | --- | --- |
| Observation volume & coverage | Strong | 21 obs, 4 schools, 7 visit days |
| Report generation / finalisation | Strong | 21 / 21 finalised |
| Report sharing within SLA | Critical | 1 / 21 shared; 16 overdue |
| Attendance discipline | Weak | 1 / 7 valid; 1 unverified |
| Session conduct & logging | Weak | 1 of 4 schools logged |
| Baseline data integrity | At risk | No follow-up dates; 90% no photo; backdated |

# 7. Consequences if Not Corrected

- Broken feedback loop (most serious): with 20 of 21 reports never reaching schools, observed teachers get no actionable feedback — the observation→feedback→improvement logic that justifies the programme collapses, and the school’s reason to host it weakens.

- Unmeasurable impact: growth = endline − baseline. Missing follow-up dates, evidence and a backdated baseline make the eventual growth number unreliable — directly threatening the headline impact Aikarthya reports to its board and funders.

- Attendance & payroll trust: 6 of 7 days end off-point and one is unverifiable; if attendance is ever tied to stipend or compliance, these records invite disputes and audit exposure.

- SLA backlog compounds: 16 reports are already overdue; each day drafts go stale and the review queue grows, making the backlog progressively less likely to be cleared.

- Unprovable work: missing photos/sessions remove the evidence trail — Aikarthya cannot substantiate to funders, board, or the school what actually happened in the field.

# 8. Recommendations

- Clear the backlog now: review and share the 16 overdue reports; treat sharing — not generation — as the completion point of an observation.

- Enforce check-out at the registered point and review the 15-Jun unverified day.

- Make 3 fields mandatory at submission: next-observation-date, student-count and a classroom photo.

- Require a session record per school for Gyanam, Grace and Safdariya; reconcile sessions-to-schools each cycle.

- Enter data on the day of the visit to end backdating and protect baseline fidelity.

Prepared for the Aikarthya Founder & M&E team from live production data on 25-Jun-2026, cross-referenced with the SkillUp programme framework. Internal analysis — confidential.